# EuroSport meeting, Bosön, Swedish National Sports Complex, October 03-05, 2010

# Workshop for evaluation of syllabi and the usability test of first prototypes of the learning materials

October 03, 2010, at 9h30 – 18h00

## Partners attending the meeting:

NSA was represented by

Evgenia Dimitrova

TUS was represented by

Slavka Tzanova

Athletic was represented by

Peter Angelov

Angel Chankov

Bosön was represented by

Ulf Lindberg

Kurt Granlund

Therese Pendother

Sheda Reed

## Opening of meeting

Ulf opened the meeting and presented in brief the history of Bosön Sports College.

## Amendments to the contracts between the beneficiary (P0) and all partners after the withdrawal of P1 were signed.

## Slavka made an overview of the activities till now and the interim report. To be discussed in details next two days.

## Kurt presented the syllabus and learning materials of the course "Sport coordinator" (new/adapted and translated material).

## A discussion on the e-learning materials on this course started. Slavka explained what is specific in e-learning materials development: self-instructional, interactive, multimedia.

Discussion on how to present the materials with multimedia for the course on “Physical exercises for aging people”. Movies, interviews, case studies etc…. Bosoen will make movies, interviews with training elder people and with the students in the course on Physical activities for elder people.

To make interviews and movies with the clients in the Fitness centres in Bulgaria as well.

## Presentation of the syllabus and learning materials of the course in Kinesitherapy by Evguenia

To change the title of the course to Physiotherapy which is the English term (Kinesitherapy used in Bulgarian is the French term).

Presentation of the whole course in ppt files.

## Evaluation of syllabi and expert review of the learning materials in both courses by the participating partners and the teachers and users from Bosoen.

## Advances in course certification procedures by Peter. EHFA meeting in march 2009. Mr. Cliff Collins.

## Mr. Collins has been invited by P3 and visited Bulgaria and the office and facilities of the Bulgarian association of health and fitness on June 3d and 4th.

Requirements for accreditaion:

- curriculum mapping the standards of EHFA and EQF for fitness instructor level 3,

- the delivery process and tutors’ team is approved by Active IQ.

Accreditation is awarded to an organisation not only to a programme.

Solution: to have accreditation of one VET provider and to deliver the certificate from this school in all participating countries. To invite the EHFA experts to assess the process of delivery during the pilot test.

## 18:00		Closing of today’s meeting

October 04, 2010, at 9h00 – 18h00

## Interim Report preparation. Technical and financial reports. Reporting and documents to be presented

Slavka made an overview of the project and the activities and results for the reported period: objectives, planned activities and outcomes, explained the financial rules for budget expenditures and the necessary documents for the reports. Then an explanation on the financial tables was done. To be discussed next day during the Flashmeeting with the partners from Germany P4 and other partners from P0.

## Tour of Bosön Swedens National Sports Complex

- The Manor House

- The Top Sport Centre

- The Sports Complex

## In the afternoon - study visit of  Friskis & Svettis - Training providers

October 05, 2010, at 9h00 – 18h00

Flashmeeting with the partners from Dortmund and Sofia

Decisions:

To start the course delivery with a common certificate delivered by all partners; to work towards an accreditation of one VET provider from the consortium and to deliver the European certificate from this school in all participating countries. To invite the EHFA experts to assess the process of delivery during the pilot test.

All partners should be ready with the financial reports and the copies of the:

- need analysis reports in English and in the partner’s language

- qualifications description in English and in the partner’s language

- syllabi of three courses in English and in the partner’s language

- learning materials developed

- financial tables for the expenditures during the first project year and copies of subcontracts, invoices and offers.

## Planning of next meetings. Other business

Next project meeting will be held in Potsdam where the large Sports School which participated in the previous LdV project. To be decided by German partners when – the first or the second week of April 2011.