# Minutes of the Fourth SOCRATES Project “OnLineMath&Science” Meeting

# ECARES, ULB, Brussels, 11 - 12 June, 2007

Monday, 11 June

Attendees:

For P1 Slavka Tzanova, TUS

Rossen Radonov, TUS

Yordanka Marcheva, TUS

For P2 Atika Cohen, ULB

Guy Mélard, ULB

For P3 Monique Vindevoghel, USTL

Jean-Marie Blondeau, USTL

For P4 Eric Olivier, UP

For P5 Catalina Martínez-Mediano, UNED

For P6 Ilonka Seikova, UCTM

Roumiana Popova, UCTM

Mr. Mélard opened the workshop.

Ms. Martínez Mediano started with the analysis of the results from the pilot test. She had all numerical data but she needs still the description of the pedagogical approach, the content, the organisation of the test. She presented the intermediate analysis results for the tests in the ULB, UP,

All partners should send to Ms. Martínez Mediano the information on the content of the courses, pedagogical organisation, e.g. exercises, practical tasks, tutorials, exams etc.

UP should send the information about the content and organisation of the test and the reflective questionnaires.

ULB should add information about the content and organisation of the test and the final marks of the knowledge test.

The results from the reflective questionnaire from UP are still not ready.

USTL should provide the results from the knowledge tests and from the pre-tests fro all 4 groups participating in the test, the attitude and reflective questionnaires for one of he groups.

UCTL should send all tests results.

TUS should send the information about the course organisation and the attitude questionnaire.

Ms. Tzanova made a review of the tasks and outcomes o be done and what is ready by now. Almost all tasks are finished and the tests also but the additional information should be sent to the evaluator.

The tasks to bi finished are:

To add additional learning sources in the library. Mrs. Vindevoghel suggested to use the library CERIMES that they have developed.

It was decided to add the information on the next courses in the Information area of the system.

The possibilities for collaborative work in mathematics are not yet found.

Course in English in Scenari, not in ForEva developed by ULB

Ms. Tzanova explained what would be necessary for the final project report, the technical and the financial one. She will send the file with the report to all partners to provide the information for their results, experiences etc.

Special attention was paid to the exploitation and dissemination activities: in high schools and secondary schools, e.g the project of UP (Rectorat of Marseille).

Demo on the Web, on CD and a brochure: to be done by TUS

Mr. Mélard presented a report of their work. Mrs. Cohen showed the Course and the tests in Chemistry that they have developed.

The problem with the English version of the course was discussed. It is a big problem to change the titles and subtitles of the different parts of the tutorials, e.g. “definition”, “exercise” etc.

Mr. Radonov explained that these are just images and he suggested to make a separate directory with images with the words in different languages.

Mrs. Vindvoghel told that they have a new version of the software and there a new functions. It was decided to try to upgrade the system.

Tuesday, 12 June

The meeting started with a discussion on the financial rules and documents to be reported and with the presentations to be prepared for the final dissemination meeting.

Mr. Mélard suggested to invite to the open workshop in Sofia partners from other projects within the EC programmes.

Ms. Marcheva and Mr. Radonov demonstrated the tests in chemistry in French and Bulgarian developed in ForEva evaluation system.

Mr. Olivier demonstrated he tests in mathematics and physics developed in ForEva by the UP.

ForEva : To make the important remark that if on the site there is a Firewall protection, ForEva is no accessible. So, the evaluators have to remove the Firewall to access For Eva. And there is a new change. The system works on the non-updated version of Java.

It was stressed again that it is not possible to perform a real experiment with a big number of students except if it is a national project imposed by the Ministry of education. We performed tests with smaller groups of 20-30 students per control and experimental group

It was decided that the last meeting will be held in Sofia on 10-11 September.

Mrs. Tzanova sent an e-mail with the tasks of each partner and she will remember be e-mail to all partners their tasks till the end of the project.